## Sheet1
8
| ID | As a… | I want to be able to… | So that… | Priority | Type | Effort | Status | Sprint
| 1 | Player | Join a game of Blackjack | I can be a player:) | Must | EPIC -Game | 10 | To be started
| 1.1 | Player | Place a bet | I take part in the game | Must | Game | 2 | To be started
| 1.11 | Player | I want to see my current credit | I know how much I can waste | Must | Game | 2 | To be started
| 1.2 | Player | Hold/Hit/Double/Split | The game is Playable | Must | Large-Game | 5 | To be started
| 1.3 | Player | Get a winning/losing screen | I can get feedback | Should | Game | 4 | To be started
| 1.4 | Player | Leave a game of Blackjack | I can stop losing money / Play another time | Must | Game | 3 | To be started
| 1.5 | New Player | Know the rules of the game | I know what to do | Must | Game | 3 | To be started
| 1.6 | Recurrent Player | Repeat the last bet | it takes less effort | Should | Game | 2 | To be started
| 1.7 | Player | View the cards I drew, and their values | I can make a wise decision | Must | Game | 4 | To be started
| 1.8 | Player | to all in a bet | possibly win large amounts of money | Must | Game | 2 | To be started
| 1.9 | Player | Want to have the possibility to buy insurance |  | Must | Game | 5 | To be started
| 2 | Developer | Have player profiles |  | Must | EPIC-Profile and Services | 8 | To be started
| 2.1 | Player | Create an account | I can use the app | Must | Profile and Services | 7 | To be started
| 2.2 | Player | Deposit Money | I can bet it | Must | Profile and Services | 3 | To be started
| 2.3 | Player | Withdraw Money | I can get my money back | Must | Profile and Services | 3 | To be started
| 2.4 | Player | Send a Message to another player | I can make friends:) | Could | Profile and Services | 10 | To be started
| 2.5 | Player | Trade credits with a player | I can give/receive credits | Could | Profile and Services | 9 | To be started
| 3 | Admin | Have multiple games occuring |  | Could | Epic - Admin Services | 10 | To be started
| 3.1 | Admin | Choose the rates of the table | I can control the profit margin | Must | Admin Services | 6 | To be started
| 3.2 | Admin | Kick a user | Avoid unwanted people | Should | Admin Services | 6 | To be started
| 3.3 | Admin | Place a dealer on a table | The table can be played on | Must | Admin Services | 5 | To be started
| 3.4 | Admin | Have a dealer that can kick a player without money | the tables are with people that want/can play | Must | Admin Services | 3 | To be started
| 3.5 | Admin | know if a player is new in the casino | I can give special offers | Should | Admin Services | 2 | To be started
| 3.6 | Admin | see the players profiles | I can manage them | Should | Admin Services | 5 | To be started
| 4 | Player | the dealers to have names | it is more personal | Should | Quality of Life | 3 | To be started
| 4.1 | Admin | allocate a dealer to a table | I have control on who is in each table | Could | Quality of Life | 5 | To be started
| 4.2 | Player | have background music | I can get hyped to gamble | Could | Quality of Life | 8 | To be started
| 4.3 | Player | mute the background music | I don't have to listen to it | Could | Quality of Life | 2 | To be started
| 4.4 | Player | Have a special sound effect when you win | i feel good when i win money | Could | Quality of Life | 2 | To be started
| 4.5 | Player | Choose the theme of the deck in the table | appreciate the cards when i play them | Could | Quality of Life | 2 | To be started
| 4.6 | Developer | Have test benches | I can weed out bugs | Must | Quality of Life-Development | 8 | To be started
Product Backlog